# Agent Resilience Project

High-Level Schedule

Prepared by: Ian Rashmika — Project Lead

Date: 24/08/2026

Phase Plan

| Key phase | Milestone | Deliverable | Expected start | Expected end |
| --- | --- | --- | --- | --- |
| Iteration 0 – Project Setup | Team and project structure established | Team charter, containment declaration, GitHub repository, hardware check | Week 1 | Week 1 |
| Iteration 1 – Model-Layer Security | Qwen safety-alignment experiment completed | Baseline results, LoRA results, refusal analysis and ASR comparison | Week 2 | Week 3 |
| Iteration 2 – Next Adversarial Testing Stage | Next tutor-provided security experiment completed | Test evidence, results and technical findings | Week 3 | Week 4 |
| Iteration 3 – Extended Security Testing | Additional attack surface evaluated | Experimental results and documented findings | Week 4 | Week 5 |
| Iteration 4 – Monitoring / Defence | Monitoring and detection environment evaluated | Wazuh or relevant monitoring evidence and findings | Week 5 | Week 6 |
| Iteration 5 – Integration & Evaluation | Findings consolidated into project solution | Integrated testing approach, evaluation results and updated toolkit/documentation | Later project stage | Before finalisation |

Critical Path

The critical path is the longest chain of dependent tasks; any slip on it slips the whole project. Path: A → B → C → E → F.

| ID | Task | Predecessor(s) | Duration (days) | Owner | On critical path? |
| --- | --- | --- | --- | --- | --- |
| A | Finalise Week 3 methodology, requirements and schedule | none | 1 | Ian | Y |
| B | Verify reference Windows lab environment and required outputs | A | 1 | Vilan | Y |
| C | Complete/verify Qwen experiment and collect technical evidence | B | 3 | Shalitha | Y |
| D | Review attack, defence and evaluation literature for planning | A | 2 | Achinthya & Nisal | N |
| E | Analyse experimental findings and update project direction | C, D | 2 | Nisal | Y |
| F | Consolidate documentation, evidence and Week 3 worklog | E | 1 | Ian | Y |

Note: the network diagram for this critical path is maintained separately in Draw.io by Vilan Nethaka (see environment/tooling document).